## Лист1
Screen function | Note | Estimated, hr
| Total: | 35.09
Localization | Makes developing a bit longer. | 3.19
TimeZones (list page) |  | 3
Add/Edit TimeZone |  | 5
Integeration TimeZones to:
Apply to Get Access |  | 2
Assignments |  | 0.3
My Applications |  | 0.3
My Approvals |  | 0.3
DoorList |  | 1
DoorList - Filtering on Pre-approved | When adding doors to a doorlist, only doors that can be preapproved | 1
Cards - Type of cards | To be added are: External and Replacement | 1
Cards - Card Expiring | Adding Expiring date to the Card table. Can be empty, meaning no expiring date. | 1
System parameters Page | There is a need for saving some system parameters. Table: SystemParameters CustomerID ( different parameters per Customer ) Field: Integer PINLength | 2
Pin code | To change to PIN code you would also need to put in the old PIN code. To apply for a new PIN just press button “Apply for new” Generate and send forgotten PIN by Email | 2
Approval Level | - Door level only creates an assignment for the Manager and Door owner - Area level only crates an assignment for the Manager and Area owner | 1
Apply for access on another’s behalf | In order to be able to prepare a card even before a new employee has started, the secretary or colleague should be able to apply for additional (special access) on the new employee’s behalf. (New Employee Flag) | 3
Delegate approval | When on vacation or other absence the approval should possible to delegate to another person for a period of time.
- Changes to the Employee table |  | 1
- My Delegation page |  | 3
My Access page | List of my access. Adding menu to user area. Sorted by City, Building, Area and Door | 2
Employee access page | List of the Managers employee’s access. Adding new menu to user area. Only shown for managers. Sorted by Employee, City, Building, Area and Door | 2
Type of assignment | Assignment can be created in two ways: Standard or Special Add Standard access to CardAccess on Request to Access | 1